NURA

Italian Wellness & Supplement Marketplace

Longevity, semplificata.

STEP-BY-STEP OPERATIONAL GUIDE

For Gianmarco & Gianmaria Paglierani

Created: 2026-03-21 | Timeline: 8-12 weeks to MVP Launch | Budget: €15,000

# TABLE OF CONTENTS

PHASE 0: Workflow Setup (Week 1, Days 1-2)

PHASE 1: Legal Foundation (Week 1-2)

PHASE 2: Digital Infrastructure (Week 1-2, parallel)

PHASE 3: Shopify Store Setup (Week 2-3)

PHASE 4: Brand Identity (Week 2-3, parallel)

PHASE 5: Product Strategy & Suppliers (Week 2-4)

PHASE 6: Legal Compliance for E-Commerce (Week 3-4)

PHASE 7: Marketing Preparation (Week 3-5)

PHASE 8: Pre-Launch Checklist (Week 5-6)

PHASE 9: Launch & First 30 Days (Week 6-8)

PHASE 10: Growth Strategy (Month 2-3)

# PHASE 0: WORKFLOW SETUP

Timeline: Week 1, Days 1-2 | ~4-5 hours combined | Total Cost: €0

Objective: Establish shared project management systems and clear role definitions

| Task | Who | Time | Cost | Priority | Dependencies | Key Steps |
| --- | --- | --- | --- | --- | --- | --- |
| 0.1 Create Notion Workspace | Both (GM lead) | 1 hour | €0 | CRITICAL | None | Sign up for Notion.so free account... Create workspace "NURA - Operations Hub"... Invite Gianmaria to workspace... |
| 0.2 Create Google Drive Folder Structure | Both (GM lead) | 30 minutes | €0 | CRITICAL | None | Create main folder: "NURA - Master Folder"... Create 6 subfolders: LEGAL, BRAND-ASSETS, SUPPLIER-CONTRACTS... Share entire folder with Gianmaria (edit access)... |
| 0.3 Communication Setup | Both | 20 minutes | €0 | CRITICAL | None | Create WhatsApp group: "NURA - Business Only"... Create Telegram group as backup... Establish email protocol for @nura.it (set up in Phase 2)... |
| 0.4 Define Roles & Responsibilities | Both | 45 minutes | €0 | CRITICAL | Tasks 0.1, 0.3 | Assign GIANMARCO: CEO/Marketing/Brand roles... Assign GIANMARIA: CTO/Operations/Logistics roles... Define shared responsibilities (legal, finance, strategy)... |
| 0.5 Schedule Weekly Sync Meetings | Both | 15 minutes | €0 | CRITICAL | Task 0.3 | Create shared calendar "NURA Weekly Sync"... Schedule recurring: Sunday 7:00-7:30 PM... Create agenda template (completed tasks, blockers, next week... |

## PHASE 0 SUMMARY

✓ Total combined effort: Week 1, Days 1-2 | ~4-5 hours combined

✓ Approximate cost: €0

# PHASE 1: LEGAL FOUNDATION

Timeline: Week 1-2 | ~15-20 hours | Mostly waiting for processing | Total Cost: €2,000-3,500

Objective: Legally establish company with all registrations, tax ID, and business structure

| Task | Who | Time | Cost | Priority | Dependencies | Key Steps |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 Choose Business Entity Type (SRL vs SRLS) | Both (GM lead) | 2 hours | €0 | CRITICAL | None | Research SRL: costs €1,500-2,000, higher credibility, invest... Research SRLS: costs €300-500, simpler, limited capital... RECOMMENDATION: Choose SRL for better supplier relationships... |
| 1.2 Find & Hire Commercialista (Accountant) | GM (lead) | 3 hours | €0 (fees from Task 1.3) | CRITICAL | Task 1.1 | Ask network for recommendations (5-10 contacts)... Search Google: "commercialista startup [city]"... Get 3-5 candidates with contact info... |
| 1.3 Initial Commercialista Meeting | Both | 2 hours | €0-100 (usually free initial consult) | CRITICAL | Task 1.2 | Meet commercialista with passports, codice fiscale, proof of... Discuss SRL formation process and timeline (1-2 weeks)... Get written quote for formation fees... |
| 1.4 Gather & Prepare Documents for SRL Formation | Both (GA organizes) | 2 hours | €0 | CRITICAL | Task 1.3 | Collect valid ID/passport copies (2 certified copies each)... Get codice fiscale for both (apply at Agenzia delle Entrate ... Collect proof of address (recent utility bill)... |
| 1.5 Visit Notary & Sign SRL Documents | Both (must attend) | 2 hours + waiting | €1,000-2,000 | CRITICAL | Task 1.4 | Schedule notary appointment (usually 3-5 days)... Bring all documents: IDs, codice fiscale, address proof... Decide on initial capital (recommend €5,000 minimum)... |
| 1.6 Register with Camera di Commercio | GM or Commercialista | 1 hour + processing | €200-300 | CRITICAL | Task 1.5 | After notary filing, commercialista typically handles this... Or go to local Camera di Commercio website... Complete "Comunicazione Unica" form... |
| 1.7 Apply for Partita IVA (Tax ID) | Commercialista | 30 min + 1 week | €0 | CRITICAL | Tasks 1.5, 1.6 | Commercialista files for Partita IVA with Agenzia delle Entr... Provide business classification (supplement e-commerce)... Processing time: 3-5 business days... |
| 1.8 Setup PEC (Certified Email) | GA (technical) | 30 minutes | €5-10/year | IMPORTANT | Task 1.7 | Go to Aruba.it and search for "PEC Business"... Select basic PEC plan (~€5-10/year)... Sign up with company info and Partita IVA... |
| 1.9 Register with INPS (Social Security) | Commercialista | 30 min + auto | €0 | IMPORTANT | Task 1.7 | Commercialista registers company with INPS... Covers social security and employer obligations... Automatic after Partita IVA, usually 1-2 weeks... |
| 1.10 Open Business Bank Account | Both (visit bank) | 1.5 hours + processing | €0-10/month | CRITICAL | Task 1.7 | RECOMMENDED: Qonto.com (€10/month, best for startups)... Go to Qonto.com/it and start application... Enter Partita IVA and company info... |
| 1.11 Create Simple Accounting Setup | GA | 1 hour | €0 | IMPORTANT | Task 1.10 | Commercialista will recommend accounting software... For MVP: use Qonto built-in accounting (free, automatic)... Create Google Sheet: Simple-P&L-Tracker... |

## PHASE 1 SUMMARY

✓ Total combined effort: Week 1-2 | ~15-20 hours | Mostly waiting for processing

✓ Approximate cost: €2,000-3,500

# PHASE 2: DIGITAL INFRASTRUCTURE

Timeline: Week 1-2 (parallel with Phase 1) | ~6-8 hours | Total Cost: €500-700/year

Objective: Secure domain, professional email, social media presence, and analytics

| Task | Who | Time | Cost | Priority | Dependencies | Key Steps |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 Register Domain Name (nura.it) | GA | 30 minutes | €10-15/year | CRITICAL | None | Go to Aruba.it (Italian registrar, best for .it)... Search "nura.it" - check availability... Register for 1 year (~€10-15)... |
| 2.2 Setup Google Workspace (Professional Email) | GA (technical), GM (config) | 1.5 hours | €18/month (€6 × 2 users + domain) | CRITICAL | Task 2.1 | Go to workspace.google.com and sign up... Choose Business Starter plan (€6/user/month)... Enter company: NURA SRL... |
| 2.3 Create Social Media Accounts | GM (lead), GA (setup) | 2 hours | €0 | CRITICAL | Task 2.2 | Create Instagram: @nura.italia with business account... Create TikTok: @nura.italia... Create Facebook page: "Nura - Wellness Italia"... |
| 2.4 Setup Google Analytics 4 (GA4) | GA | 45 minutes | €0 | IMPORTANT | Task 2.2 | Go to analytics.google.com and sign up... Create property: "Nura Main Website"... Set timezone: Europe/Rome, currency: EUR... |
| 2.5 Setup Meta Business Suite | GA (technical), GM (brand) | 1.5 hours | €0 | IMPORTANT | Task 2.3 | Go to business.facebook.com and sign up... Create Business: "Nura SRL"... Connect Instagram account: @nura.italia... |
| 2.6 Setup GDPR Compliance Tool (iubenda) | GA (setup), GM (review) | 1 hour | €0 trial, then €29/year | IMPORTANT | Tasks 2.1, 2.2 | Go to iubenda.com (Italian GDPR specialist)... Sign up with info@nura.it... Choose Essential plan (€29/year)... |

## PHASE 2 SUMMARY

✓ Total combined effort: Week 1-2 (parallel with Phase 1) | ~6-8 hours

✓ Approximate cost: €500-700/year

# PHASE 3: SHOPIFY STORE SETUP

Timeline: Week 2-3 | Total Cost: €500-1,500 | ~25-30 hours

Objective: Create fully functional e-commerce store with brand identity, payment processing, and fulfillment setup.

Task 3.1: Create Shopify Account & Choose Plan (€36/month Basic) - 1 hour

Task 3.2: Connect Custom Domain (nura.it to Shopify) - 1 hour

Task 3.3: Choose & Customize Theme (use free Dawn theme, set colors #1a1a1a #2d5016) - 3-4 hours

Task 3.4: Create Essential Pages (Homepage, Chi Siamo, Contatti, FAQ, Blog) - 2-3 hours

Task 3.5: Create Legal Pages - CRITICAL (Privacy, Cookie, Terms, Returns, Sales Conditions) - 2 hours

Task 3.6: Setup Payment Gateways (Shopify Payments + PayPal) - 1.5 hours

Task 3.7: Setup Shipping Configuration (Italy €3, 2-3 days) - 1.5 hours

Task 3.8: Configure Tax Rules (IVA 22% standard, 10% for some supplements) - 1 hour

Task 3.9: Install Essential Shopify Apps (Klaviyo, Judge.me, Google, Meta, Recharge) - 1.5 hours

Task 3.10: Integration with Analytics (GA4 + Meta Pixel) - 1 hour

## PHASE 3 SUMMARY

✓ Professional Shopify store live at nura.it

✓ All pages and legal documentation complete

✓ Payment processing active and tested

✓ Analytics tracking configured and verified

# PHASE 4: BRAND IDENTITY

Timeline: Week 2-3 | ~8-10 hours | Total Cost: €300-800

Objective: Establish visual identity and create reusable brand assets

## KEY TASKS & SUBTASKS

Design professional logo (Canva Pro €12/month or Fiverr €50-200)

Finalize color palette (primary #1a1a1a, accent #2d5016)

Select typography (Poppins Bold for headings, Inter for body)

Create brand photography style guide

Design social media templates in Canva

Order packaging materials (branded tape, thank you cards, tissue paper)

## PHASE 4 SUMMARY

Timeline: Week 2-3 | ~8-10 hours

Investment: €300-800

Objective: Establish visual identity and create reusable brand assets

# PHASE 5: PRODUCT STRATEGY & SUPPLIERS

Timeline: Week 2-4 | ~20-25 hours | Total Cost: €500-1,000

Objective: Establish supplier relationships and create initial product catalog

## KEY TASKS & SUBTASKS

Research Italian supplement regulations (D.Lgs. 169/2004)

Identify 5-8 supplier brands (AG1, Foodspring, Bulk, MyProtein, Solgar, Named)

Contact suppliers with pitch emails (negotiate dropship, 30-40% margins)

Create supplier comparison spreadsheet

Create product listings with Italian descriptions and pricing

Upload 15-20 initial products to Shopify for MVP

## PHASE 5 SUMMARY

Timeline: Week 2-4 | ~20-25 hours

Investment: €500-1,000

Objective: Establish supplier relationships and create initial product catalog

# PHASE 6: LEGAL COMPLIANCE FOR E-COMMERCE

Timeline: Week 3-4 | ~10-12 hours | Total Cost: €300-500

Objective: Ensure full legal compliance for Italian e-commerce operations

## KEY TASKS & SUBTASKS

GDPR compliance checklist & data processing agreement

Consumer rights documentation (14-day returns, transparent pricing)

Supplement labeling requirements & Ministero della Salute notification

Professional liability insurance quote

Hire lawyer to review all legal pages (€300-500 one-time)

Finalize all terms and conditions

## PHASE 6 SUMMARY

Timeline: Week 3-4 | ~10-12 hours

Investment: €300-500

Objective: Ensure full legal compliance for Italian e-commerce operations

# PHASE 7: MARKETING PREPARATION

Timeline: Week 3-5 | ~18-22 hours | Total Cost: €100-500

Objective: Prepare launch campaign materials and marketing infrastructure

## KEY TASKS & SUBTASKS

Create 30 Instagram posts + captions in advance

Plan TikTok strategy (short-form wellness videos)

Build Klaviyo email sequences (welcome, abandoned cart, post-purchase)

Create list of 20 Italian micro-influencers (1K-50K followers)

Plan launch campaign: 247 waitlist, 15% early bird discount, referral program

Setup Meta Ads Manager with €20/day test budget

## PHASE 7 SUMMARY

Timeline: Week 3-5 | ~18-22 hours

Investment: €100-500

Objective: Prepare launch campaign materials and marketing infrastructure

# PHASE 8: PRE-LAUNCH CHECKLIST

Timeline: Week 5-6 | ~12-15 hours | Total Cost: €0

Objective: Comprehensive quality assurance before public launch

## KEY TASKS & SUBTASKS

Test entire purchase flow (desktop + mobile)

Test all payment methods & email confirmations

Mobile responsiveness audit

Page speed optimization (target <3 seconds)

SEO setup: Google Search Console, sitemap submission

Customer service protocols & email templates ready

## PHASE 8 SUMMARY

Timeline: Week 5-6 | ~12-15 hours

Investment: €0

Objective: Comprehensive quality assurance before public launch

# PHASE 9: LAUNCH & FIRST 30 DAYS

Timeline: Week 6-8 | variable | Total Cost: €500-2,000

Objective: Execute soft launch and optimize based on real customer data

## KEY TASKS & SUBTASKS

Soft launch to 247 waitlist members

Monitor & fix technical issues in real-time

Daily: order fulfillment, customer support, social posting

Weekly: analyze metrics, optimize ads

Track KPIs: conversion rate, AOV, CAC, email open rates

Gather customer feedback for improvements

## PHASE 9 SUMMARY

Timeline: Week 6-8 | variable

Investment: €500-2,000

Objective: Execute soft launch and optimize based on real customer data

# PHASE 10: GROWTH STRATEGY

Timeline: Month 2-3 | ongoing | Total Cost: €1,000-3,000

Objective: Scale operations and expand market reach

## KEY TASKS & SUBTASKS

Activate subscription model (Recharge for recurring orders)

Launch loyalty program (points, referral bonuses)

Expand product catalog to 50+ SKUs

Content marketing: blog posts, YouTube wellness content

Explore health assessment partnerships (blood testing)

Analyze LTVCAC ratio and optimize acquisition channels

## PHASE 10 SUMMARY

Timeline: Month 2-3 | ongoing

Investment: €1,000-3,000

Objective: Scale operations and expand market reach

# KEY METRICS TO TRACK

Conversion Rate: (Orders / Visitors) × 100 | Target: 1-2% for MVP

Average Order Value (AOV): Total Revenue / Total Orders | Target: €50-75

Customer Acquisition Cost (CAC): Total Marketing Spend / New Customers | Target: <€20

Email Open Rate: (Opens / Emails Sent) × 100 | Target: 25-35%

Email Click-Through Rate: (Clicks / Emails Sent) × 100 | Target: 3-5%

Return on Ad Spend (ROAS): Revenue from Ads / Ad Spend | Target: 3:1 or higher

Customer Lifetime Value (LTV): Avg Revenue × Retention Period | Target: €150-300

# DETAILED BUDGET BREAKDOWN (€15,000 Total)

| Category | Items | Estimated Cost | Notes |
| --- | --- | --- | --- |
| LEGAL & REGISTRATION | SRL Formation, Commercialista, Bank Account, PEC, Partita IVA | €2,000-3,500 | One-time + annual |
| DIGITAL INFRASTRUCTURE | Domain, Google Workspace, Shopify, iubenda | €500-700/year | Annual recurring |
| BRAND & DESIGN | Logo, Canva Pro, Packaging, Social Templates | €300-800 | One-time |
| SHOPIFY & APPS | Shopify Basic €36/month, Klaviyo, Judge.me, Meta/Google channels | €400-500/month | Core + apps |
| MARKETING (Phase 7) | Meta Ads, Influencer outreach, Content creation | €1,000-2,000 | Variable |
| PRODUCT INVENTORY | Supplier orders, Product photos, Data entry | €2,000-5,000 | Depends on MOQ |
| MISC & CONTINGENCY | Insurance, Unexpected costs, Buffer | €500-1,000 | Safety net |

# SUCCESS FACTORS & KEY TIPS

Speed Over Perfection: Launch with 15-20 products, not 100. Iterate based on demand.

Focus on Waitlist: Convert your 247 waitlist members first with special launch offers.

Daily Operations: Spend 15 minutes each morning checking orders, emails, analytics.

Weekly Sync: Sunday 30-min meeting: review KPIs, blockers, next week priorities.

Document Everything: Every decision, meeting, supplier contact, bug fix - document it.

Parallel Execution: While waiting for notary, start supplier research. Maximize time.

Budget Discipline: €15K is runway. Track daily, optimize weekly, cut ruthlessly.

Early Customer Feedback: Call waitlist members in Week 2 - learn what they actually want.

This guide is a living document. Update it weekly as you learn and adapt.

Document Version: 1.0 | Created: 2026-03-21 | For: Gianmarco & Gianmaria Paglierani